## Spacing App_Log
Task ID | Micro-Utility Node | PDCA Phase | Optimization Domain | Target Keyword / Query Cluster | Proposed Action / Change Specification | Baseline Metrics (Imp / Clicks / CTR) | Average Search Position | Pageviews / Week | Time on Page | Trigger Outcome | Breakout Flag | Impl. Target Date | Status | Review Target Date | Post-Impl. Metrics | Delta / Impact Outcome | Product Level Status | Owner | Notes / Technical Dependencies
OPT-SPC-001 | Spacing App | Plan | On-Page SEO (Title Tag) | baluster spacing template, spindle spacing calculator | Update <title> tag to: Equal Spacing Calculator ¦ Baluster, Spindle & Picket Layout Tool | 13 Imp / 0 Clicks / 0.0% | 18.4 | 0 | 0s | Hold (Fails CTR >= 1% & PV >= 30) | Standard (Position <= 40) | 2026-07-23 | Planned | 2026-08-05 | — | Pending | Keep (Active Demand) | Operations Lead | Direct title alignment with top non-converting GSC queries. GA4 telemetry required for PV/Time.
OPT-SPC-002 | Spacing App | Plan | On-Page SEO (Meta Description) | calculating baluster spacing on stairs, picket spacing calculator | Implement meta description: Calculate exact equal spacing for stair balusters, deck spindles, and pickets. Free, zero-telemetry client-side layout tool with instant visual preview. | 10 Imp / 0 Clicks / 0.0% | 22.1 | 0 | 0s | Hold (Fails CTR >= 1% & PV >= 30) | Standard (Position <= 40) | 2026-07-23 | Planned | 2026-08-05 | — | Pending | Keep (Active Demand) | Operations Lead | CTR hook targeting intent-driven searchers. Zero external script overhead.
OPT-SPC-003 | Spacing App | Plan | UI / On-Page Content | stair baluster calculator, equal spacing calculator app | Add UI preset toggles and semantic micro-headings ("Stair Baluster Mode", "Deck Picket Mode") to reinforce keyword density | 2 Imp / 0 Clicks / 0.0% | 31 | 0 | 0s | Hold (Fails CTR >= 1% & PV >= 30) | Standard (Position <= 40) | 2026-07-25 | Backlog | 2026-08-05 | — | Pending | Keep (Active Demand) | Operations Lead | Zero-dependency DOM updates; ensures UI reflects query terminology.

## Tasks
Task Statement | Task | Status
Measurement & Project Work Performance Domains | Deploy the updated PDCA Optimization Ledger schema to the Spacing App workbook repository. | Done
Measurement & Project Work Performance Domains | Confirm GA4/analytics event tracking is wired to collect weekly pageview and time-on-page metrics, and execute task OPT-SPC-001 by updating on-page metadata prior to the August 5, 2026 gate review. | Pending
| Formally Log Completion of GSC Re-Indexing Request (OPT-SPC-001/002) and Initiate Mandatory Production Freeze Until August 5, 2026 Performance Review (WBS Item 1.3.10) | Done
| Pull the 10-day post-fix GSC dataset to evaluate performance against the baseline targets on sheet of same name. | After August 5

## Deployment SOP
Deployment Method | How It Works
GitHub Deployment (Your Active Pipeline) | You git push > GitHub notifies Netlify > Netlify builds and deploys in the cloud automatically.
EXECUTION SEQUENCE IN POWERSHELL
git add index.html spacing-calculator-build/index.html
git commit -m "OPT-SPC-001/002: Deploy updated title and meta description to root index.html"
git push origin main
Verification Check
(Invoke-WebRequest -Uri "https://spacing.headsup-consulting.com/" -UseBasicParsing).Content ¦ Select-String -Pattern "<title>", "description"
Expected Output Upon Success
<title>Baluster & Spindle Spacing Calculator (Inches & mm) ¦ Equal Gap Tool</title> <meta name="description" content="Free spacing calculator for stair balusters, deck pickets & spindles. Meets the common 4-inch / 100mm sphere-gap guideline — always confirm against your local building code.">

## Baseline_Target
Metric | Target Baseline | Decision Action
CTR (Click-Through Rate) | $\ge 1.0\%$ | PASS: Qualifies asset for global expansion evaluation (PSPDG Sec 6.2).
CTR (Click-Through Rate) | $< 1.0\%$ | HOLD: Requires secondary meta/snippet iteration before scaling.
Impression Volume | Trend Stable or Increasing | Confirms Googlebot retained topical index placement.
Procedure
After August 5th send this baseline data plus GSC new data to Gemini chat "Breakout Apps"